## Sheet1
Validation Log
Program | Issue | Correction | Discussed with AH? | Renamed? | Future?
XML Input checker | Extra datastep which would overwrite what was inputted | Removed | Yes 11/07/2017 | Dummy suffix | Ensure correct master is used following validation
XML Input checker | Comparing labels for AE and SAE but not for groups | label added to grps checker | Yes 11/07/2017
XML Input checker | SOC length doesn't match what is written in guideline | Changed in 100 in guideline | Yes 11/07/2017
EUTCT_fmts | Version number has since been updated and missing "product issues" | Updated to new version number, added additional SOC | Yes 11/07/2017 | KLR Suffix | Need to think about how to implement this in the future, how will we know version has been updated? | 1) Individual needs to upload to eudract, 2) Individual checks version number in formats document. 3)Individual uses link in WI to check we've got the correct version number 4)Individual follows steps in work instruction to correct new thing AND SUSPERCEDES THE OLD by prefixing version number.
EUTCT_fmts | Links no longer work | Updated to say "refer to WI" since it will have to be included. |  | KLR Suffix |  | http://eutct.ema.europa.eu/eutct/displayWelcome.do -> RMS -> view lists -> Medical Dictionary For Regulatory Activities
XML Input checker | Not all mandatory variables are included in checks: SAE = Term isn't checked AssType is wrong. PatSn is wrong. Occur Occurtrt is wrong. AE = Term isn't checked Asstype is wrong. PatSn is wrong.Occur is wrong. Missing SOC is suspicious in both. | Updated to correct variables | Yes 11/07/2017 | Dummy suffix
XML Input Checker | Where is Scenario C officially checked? | Added a different section and edited current to only check for missing. | Yes 11/07/2017 | Dummy suffix
XML Input Checker | Check 4 is not working properly: Dset is never called EudractAE, changed merge to a set for set check5, missing groups check doesn't work properly. | Added in if b then dset="EudractAE" | Yes 12/08/2017 | Dummy suffix
XML Input Checker | Check 5 was not red in the log | Added "ERR" "OR:" |  | Dummy suffix
XML Creator | non-systematic assessment type was not coded correctly. | Added non_ to make it work correctly and added an additional scenario to check it worked. | Yes 13/07/2017 | Dummy Suffic